## 00_Home
PROJECT AURA · AI-Powered Project Management
ABC Retail Corporation — GenAI Customer Analytics Platform
PROJECT SUMMARY |  | PROJECT HEALTH
Project Name | ABC Retail Corporation — AI Customer Analytics | Overall Status | AMBER — review milestone tracker
Client | ABC Retail Corporation | Schedule | AMBER — update actuals in Task Plan
Service Provider | XYZ Technology Solutions | Budget | GREEN — update in Budget Tracker
Project Type | GenAI / AI Implementation | Resources | AMBER — all at 100%, review allocation
Delivery Model | Fixed Price | Risks | RED — 6 open risks, none mitigated
Start Date | 2026-07-08
End Date | 2026-10-28
Duration | 16 weeks
Team Size | 5
PM
Last Updated | 2026-07-19
NAVIGATION
01_Executive_Dashboard | Executive KPIs, budget burn, schedule health
02_Project_Charter | Project scope, objectives, assumptions, constraints
03_Detailed_Task_Plan | WBS task list with actuals, dependencies, % complete
04_Budget_Tracker | Cost plan vs actuals, burn rate, variance ← NEW
05_Milestone_Tracker | Key milestones with RAG status and variance
06_Resource_Plan | Weekly allocation, utilisation flags
07_RAID_Register | Risks, Assumptions, Issues, Dependencies
08_RACI_Matrix | Responsibility assignments
09_Weekly_Status | Weekly status reports (fill every Friday) ← NEW
10_Change_Log | Scope, schedule, budget change requests ← NEW

## Executive_Dashboard
EXECUTIVE PROJECT DASHBOARD
KEY METRICS
Schedule % |  | Budget Burn % |  | Milestones Done |  | Open Risks |  | Open Issues
0 |  | 0 |  | 0 |  | 0 |  | 0
PHASE SUMMARY
Phase | Start | End | Duration | Owner | Status | % Complete | RAG
Initiation | 2026-07-08 | 2026-07-15 | 1w | PM | Planned | 0% | AMBER
Discovery | 2026-07-15 | 2026-07-29 | 2w | BA | Planned | 0% | AMBER
Design | 2026-07-29 | 2026-08-12 | 2w | Architect | Planned | 0% | AMBER
Development | 2026-08-12 | 2026-09-16 | 5w | Dev Lead | Planned | 0% | AMBER
Testing | 2026-09-16 | 2026-09-30 | 2w | QA Lead | Planned | 0% | AMBER
UAT | 2026-09-30 | 2026-10-07 | 1w | Client PM | Planned | 0% | AMBER
Deployment | 2026-10-07 | 2026-10-14 | 1w | DevOps | Planned | 0% | AMBER
Hypercare | 2026-10-14 | 2026-10-28 | 2w | PM | Planned | 0% | AMBER
TOP RISKS (from RAID Register)
ID | Description | Impact | Probability | Score | Owner | Mitigation | Status
ID | Type | Description | Impact (1-5) |  | Risk Score | Owner | Mitigation / Action
R1 | Risk | Requirement scope creep — client adds features mid-sprint | 4 |  | 12 | PM | Conduct detailed requirements workshops; freeze scope after sign-off (Week 2). All changes go through formal change request.
R2 | Risk | Integration failures with existing retail data systems | 4 |  | 12 | Tech Lead | Define API contracts in Week 3. Run integration smoke tests in each sprint. Maintain a fallback data-sync approach.
R3 | Risk | AI model performance below 85% accuracy threshold | 5 |  | 10 | Dev Lead | Run baseline model benchmarks in Discovery. Allocate 1 extra sprint buffer for model tuning if needed.
R4 | Risk | Security vulnerabilities in AI API endpoints | 5 |  | 10 | DevOps | Include security audit in testing phase (Week 11). Follow OWASP API security checklist. Penetration test before UAT.
R5 | Risk | Client data delivery delays blocking development | 4 |  | 12 | PM | Formally request data assets in Week 1. Escalate to sponsor if not received by Week 3.

## Detailed_Task_Plan
DETAILED TASK PLAN (WBS)
Blue cells = fill in ¦ Green cells = formula (do not edit) ¦ Status dropdown: Not Started / In Progress / Done / On Hold / Cancelled
WBS | Phase | Task / Deliverable | Owner | Predecessor | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | % Complete | Status | Comments
1.0 | Initiation | Project kickoff | PM |  | 2026-07-08 | 2026-07-15 |  |  | 7 | 0 | 0% | Not Started
1.1 | Initiation | Project charter sign-off | PM | 1.0 | 2026-07-08 | 2026-07-12 |  |  | 4 | 0 | 0% | Not Started
1.2 | Initiation | Stakeholder register | PM | 1.0 | 2026-07-08 | 2026-07-15 |  |  | 7 | 0 | 0% | Not Started
2.0 | Discovery | Requirements gathering | BA | 1.0 | 2026-07-15 | 2026-07-29 |  |  | 14 | 0 | 0% | Not Started
2.1 | Discovery | Current-state data assessment | BA | 1.1 | 2026-07-15 | 2026-07-22 |  |  | 7 | 0 | 0% | Not Started
2.2 | Discovery | AI use-case definition | BA | 2.1 | 2026-07-22 | 2026-07-29 |  |  | 7 | 0 | 0% | Not Started
2.3 | Discovery | Requirements doc sign-off | Client PM | 2.2 | 2026-07-29 | 2026-07-29 |  |  | 0 | 0 | 0% | Not Started
3.0 | Design | Solution architecture | Architect | 2.0 | 2026-07-29 | 2026-08-12 |  |  | 14 | 0 | 0% | Not Started
3.1 | Design | Data pipeline design | Architect | 2.2 | 2026-07-29 | 2026-08-05 |  |  | 7 | 0 | 0% | Not Started
3.2 | Design | AI model selection & design | Architect | 2.2 | 2026-07-29 | 2026-08-05 |  |  | 7 | 0 | 0% | Not Started
3.3 | Design | API contract definition | Tech Lead | 3.1 | 2026-08-05 | 2026-08-12 |  |  | 7 | 0 | 0% | Not Started
3.4 | Design | Design spec sign-off | Client PM | 3.3 | 2026-08-12 | 2026-08-12 |  |  | 0 | 0 | 0% | Not Started
4.0 | Development | Core development | Dev Lead | 3.0 | 2026-08-12 | 2026-09-16 |  |  | 35 | 0 | 0% | Not Started
4.1 | Development | Data ingestion pipeline | Developer | 3.1 | 2026-08-12 | 2026-08-26 |  |  | 14 | 0 | 0% | Not Started
4.2 | Development | AI model training pipeline | Dev Lead | 3.2 | 2026-08-12 | 2026-09-02 |  |  | 21 | 0 | 0% | Not Started
4.3 | Development | API layer development | Developer | 3.3 | 2026-08-26 | 2026-09-09 |  |  | 14 | 0 | 0% | Not Started
4.4 | Development | Dashboard UI development | Developer | 4.3 | 2026-09-02 | 2026-09-16 |  |  | 14 | 0 | 0% | Not Started
4.5 | Development | Code review & quality gate | Tech Lead | 4.4 | 2026-09-09 | 2026-09-16 |  |  | 7 | 0 | 0% | Not Started
5.0 | Testing | QA testing | QA Lead | 4.0 | 2026-09-16 | 2026-09-30 |  |  | 14 | 0 | 0% | Not Started
5.1 | Testing | Unit & integration testing | QA Lead | 4.5 | 2026-09-16 | 2026-09-23 |  |  | 7 | 0 | 0% | Not Started
5.2 | Testing | Performance & load testing | QA Lead | 5.1 | 2026-09-23 | 2026-09-30 |  |  | 7 | 0 | 0% | Not Started
5.3 | Testing | Security audit | DevOps | 5.1 | 2026-09-23 | 2026-09-30 |  |  | 7 | 0 | 0% | Not Started
6.0 | UAT | User acceptance testing | Client PM | 5.0 | 2026-09-30 | 2026-10-07 |  |  | 7 | 0 | 0% | Not Started
6.1 | UAT | UAT test execution | Client PM | 5.3 | 2026-09-30 | 2026-10-05 |  |  | 5 | 0 | 0% | Not Started
6.2 | UAT | Bug fixes from UAT | Dev Lead | 6.1 | 2026-10-05 | 2026-10-07 |  |  | 2 | 0 | 0% | Not Started
6.3 | UAT | UAT sign-off | Client PM | 6.2 | 2026-10-07 | 2026-10-07 |  |  | 0 | 0 | 0% | Not Started
7.0 | Deployment | Production deployment | DevOps | 6.0 | 2026-10-07 | 2026-10-14 |  |  | 7 | 0 | 0% | Not Started
7.1 | Deployment | Deployment runbook prep | DevOps | 6.3 | 2026-10-07 | 2026-10-10 |  |  | 3 | 0 | 0% | Not Started
7.2 | Deployment | Go-live deployment | DevOps | 7.1 | 2026-10-14 | 2026-10-14 |  |  | 0 | 0 | 0% | Not Started
7.3 | Deployment | Go-live sign-off | PM | 7.2 | 2026-10-14 | 2026-10-14 |  |  | 0 | 0 | 0% | Not Started
8.0 | Hypercare | Hypercare & support | PM | 7.0 | 2026-10-14 | 2026-10-28 |  |  | 14 | 0 | 0% | Not Started
8.1 | Hypercare | Daily stand-ups & monitoring | PM | 7.3 | 2026-10-14 | 2026-10-28 |  |  | 14 | 0 | 0% | Not Started
8.2 | Hypercare | Lessons learned session | PM | 8.1 | 2026-10-24 | 2026-10-28 |  |  | 4 | 0 | 0% | Not Started
8.3 | Hypercare | Project closure report | PM | 8.2 | 2026-10-28 | 2026-10-28 |  |  | 0 | 0 | 0% | Not Started
Formulas:
Planned Days = IFERROR(DATEDIF([Planned Start],[Planned End],"D"),"")
Actual Days = IFERROR(DATEDIF([Actual Start],[Actual End],"D"),"")

## Budget_Tracker
BUDGET TRACKER · NEW
CONTRACT SUMMARY
Total Contract Value ($) | 250000 | ← update this
Contingency Reserve ($) | 25000 | ← typical 10%
Baseline Budget ($) | 225000
RESOURCE COST PLAN vs ACTUALS
Resource | Role | Daily Rate ($) | Planned Days | Planned Cost ($) | Actual Days | Actual Cost ($) | Variance ($) | Variance %
PM_1 | PM | 650 | 80 | 52000 | 0 | 0 | 52000 | 100%
TechLead_1 | Tech Lead | 750 | 80 | 60000 | 0 | 0 | 60000 | 100%
Developer_1 | Developer | 600 | 80 | 48000 | 0 | 0 | 48000 | 100%
QAEngineer_1 | QA Engineer | 550 | 60 | 33000 | 0 | 0 | 33000 | 100%
DevOps_1 | DevOps | 650 | 50 | 32500 | 0 | 0 | 32500 | 100%
TOTALS |  |  | 350 | 225500 | 0 | 0 | 225500 | 100%
BURN RATE SUMMARY
Total Planned Cost ($) | 225500
Total Actual Cost ($) | 0
Cost Variance ($) | 0
Budget Burn % | 0%
Remaining Budget ($) | 225000

## Milestone_Tracker
MILESTONE TRACKER
ID | Milestone | Owner | Planned Date | Actual Date | Status | Priority | Days Variance | Remarks
M1 | Project Kickoff | PM | 2026-07-08 |  | Complete | High
M2 | Requirements Sign-off | BA | 2026-07-29 |  | Planned | High
M3 | Design Review & Approval | Architect | 2026-08-12 |  | Planned | High
M4 | Development Complete | Dev Lead | 2026-09-16 |  | Planned | High
M5 | QA Testing Complete | QA Lead | 2026-09-30 |  | Planned | High
M6 | UAT Sign-off | Client PM | 2026-10-07 |  | Planned | High
M7 | Go-Live | DevOps | 2026-10-14 |  | Planned | Critical
M8 | Hypercare Complete | PM | 2026-10-28 |  | Planned | Medium
Formulas:
Days Variance = IFERROR(IF([Actual Date]="","",DATEDIF([Planned Date],[Actual Date],"D")),"")

## Resource_Plan
RESOURCE PLAN · Weekly Allocation
Resource | Role | Dept | Start Date | End Date | Planned Hrs | Actual Hrs | Allocation % | Utilisation % | Flag
PM_1 | PM | Delivery | 2026-07-08 | 2026-10-28 | 480 | 0 | 80% | 0% | OK
TechLead_1 | Tech Lead | Engineering | 2026-07-08 | 2026-10-28 | 480 | 0 | 80% | 0% | OK
Developer_1 | Developer | Engineering | 2026-07-08 | 2026-10-28 | 480 | 0 | 80% | 0% | OK
QAEngineer_1 | QA Engineer | Quality | 2026-07-08 | 2026-10-28 | 360 | 0 | 80% | 0% | OK
DevOps_1 | DevOps | Engineering | 2026-07-08 | 2026-10-28 | 300 | 0 | 80% | 0% | OK
Note: Max recommended allocation is 80% to allow for meetings, admin, and leave. Flag highlights resources >90%.

## RAID_Register
RAID REGISTER · Risks · Assumptions · Issues · Dependencies
RISKS
ID | Type | Description | Impact (1-5) | Probability (1-5) | Risk Score | Owner | Mitigation / Action | Status
R1 | Risk | Requirement scope creep — client adds features mid-sprint | 4 | 3 | 12 | PM | Conduct detailed requirements workshops; freeze scope after sign-off (Week 2). All changes go through formal change request. | Open
R2 | Risk | Integration failures with existing retail data systems | 4 | 3 | 12 | Tech Lead | Define API contracts in Week 3. Run integration smoke tests in each sprint. Maintain a fallback data-sync approach. | Open
R3 | Risk | AI model performance below 85% accuracy threshold | 5 | 2 | 10 | Dev Lead | Run baseline model benchmarks in Discovery. Allocate 1 extra sprint buffer for model tuning if needed. | Open
R4 | Risk | Security vulnerabilities in AI API endpoints | 5 | 2 | 10 | DevOps | Include security audit in testing phase (Week 11). Follow OWASP API security checklist. Penetration test before UAT. | Open
R5 | Risk | Client data delivery delays blocking development | 4 | 3 | 12 | PM | Formally request data assets in Week 1. Escalate to sponsor if not received by Week 3. | Open
R6 | Risk | Testing coverage gaps leading to production defects | 4 | 2 | 8 | QA Lead | Develop test plan with 90% coverage target. Automate regression suite. Include performance and load tests. | Open
ASSUMPTIONS
ID | Type | Description | Impact (1-5) | Probability (1-5) | Risk Score | Owner | Mitigation / Action | Status
A1 | Assumption | Client will provide access to production data environment by end of Week 2 | 3 | 2 | 6 | PM | Confirm in kickoff meeting. Raise as issue if not received by 2026-07-22. | Open
A2 | Assumption | API schema and documentation are available and stable at project start | 3 | 3 | 9 | Tech Lead | Validate in Discovery. Raise as issue immediately if schema is incomplete. | Open
A3 | Assumption | Client product owner available minimum 4 hrs/week for reviews and approvals | 4 | 2 | 8 | PM | Confirm availability in kickoff. Include in project charter sign-off. | Open
A4 | Assumption | Staging environment mirrors production; no major config differences | 4 | 2 | 8 | DevOps | Conduct environment audit in Week 1. Document any deltas. | Open
A5 | Assumption | Client responds to review and sign-off requests within 3 business days | 4 | 3 | 12 | PM | Include SLA in project charter. Track in weekly status report. | Open
ISSUES
ID | Type | Description | Impact (1-5) | Probability (1-5) | Risk Score | Owner | Mitigation / Action | Status
I1 | Issue | [Add issues here as they arise] | 0 | 0 | 0 | TBD | [Add mitigation action] | Open
DEPENDENCIES
ID | Type | Description | Impact (1-5) | Probability (1-5) | Risk Score | Owner | Mitigation / Action | Status
D1 | Dependency | Client data team must deliver cleaned dataset before AI model training (Week 4) | 4 | 3 | 12 | BA | Confirm data readiness date with client in Week 1. Monitor weekly. | Open
D2 | Dependency | Client IT must provision staging environment before development begins (Week 2) | 4 | 3 | 12 | DevOps | Request provisioning in kickoff. Chase weekly if not received by Week 2. | Open
D3 | Dependency | Third-party AI platform licence must be procured before model training (Week 3) | 3 | 2 | 6 | PM | Raise purchase request in Week 1 to avoid procurement delays. | Open

## RACI_Matrix
RACI MATRIX · Responsible · Accountable · Consulted · Informed
R = Responsible — does the work |  | A = Accountable — final authority |  | C = Consulted — provides input |  | I = Informed — kept in the loop
Activity | PM | BA | Architect | Dev Lead | QA Lead | DevOps | Client PM
Project Kickoff | A | C | C | C | C | I | C
Requirements Gathering | A | R | C | C | C | I | C
Solution Architecture | I | C | R | C | I | C | A
Project Plan Approval | A | I | I | I | I | I | C
Data Pipeline Development | I | C | C | R | I | C | I
AI Model Development | I | C | A | R | I | C | I
API Development | I | I | C | R | I | C | I
Code Review | I | I | A | R | C | C | I
Test Plan Creation | I | C | C | C | R | C | A
QA Testing Execution | I | I | C | C | R | C | I
Security Audit | I | I | C | C | C | R | I
UAT Facilitation | A | C | I | I | C | I | R
UAT Sign-off | I | I | I | I | I | I | A
Deployment Planning | A | I | C | C | I | R | I
Go-Live Execution | A | I | C | C | C | R | I
Go-Live Sign-off | A | I | I | I | I | I | R
Hypercare Monitoring | R | I | C | C | C | C | I
Change Request Management | A | C | C | I | I | I | R
Risk Management | R | C | C | C | C | C | A
Status Reporting | R | I | I | I | I | I | A
Lessons Learned | R | C | C | C | C | C | A
AI Bias & Ethics Review | I | C | R | C | I | I | A
Data Governance Compliance | I | R | C | I | I | C | A
Project Closure Report | R | C | I | I | I | I | A

## Change_Log
CHANGE LOG · Record all scope, schedule, and budget changes
Every change to scope, timeline, or budget must be logged here and approved before implementation.
CR # | Date Raised | Raised By | Type | Description | Impact on Schedule | Impact on Budget ($) | Approved By | Approval Date | Status | New Baseline Date
CR-001 | 2026-07-08 | PM | Scope | [Example] Add real-time dashboard refresh | 0 days | $0 | Sponsor | 2026-07-10 | Approved | 2026-07-08