## 00_Home
PROJECT AURA
AI-Generated Project Management Workbook
PROJECT SUMMARY
Project Name | Client Name (To be provided)
Client Name | Client Name (To be provided)
Project Type | GenAI / AI Implementation
Start Date | 2026-07-07
End Date | 2026-10-06
Duration | 13 weeks
Estimated Team Size | 9
Delivery Model | Hybrid
Generated Date | 2026-06-28 13:01:44
NAVIGATION
01_Executive_Dashboard | Executive KPIs and project health
02_AI_Project_Summary | AI-generated insights and recommendations
03_Project_Details | Project charter and detailed information
04_Project_Roadmap | Phase-level timeline and milestones
05_Detailed_Project_Plan | Task-level project plan
06_Gantt_Chart | Visual timeline and critical path
07_Milestone_Tracker | Key milestones and deliverables
08_Resource_Plan | Resource allocation and capacity
09_RAID_Register | Risks, assumptions, issues, dependencies
10_RACI_Matrix | Responsibility assignments
11_Weekly_Status | Progress tracking and status
Generated by Project Aura ¦ 2026-06-28 13:01:44

## 01_Executive_Dashboard
EXECUTIVE PROJECT DASHBOARD
Generated: 2026-06-28 13:01:44
Project Duration |  | Team Size | Risk Count |  | Deliverables
13 weeks |  | 9 people | 6 |  | 3
PROJECT HEALTH
RED - High Risk
KEY METRICS
Total Team Members | 5 |  | Total Risks | 6
Total Dependencies | 0 |  | Confidence Score | 70%
TOP RISKS
Risk | Severity | Mitigation
Requirement scope creep | Medium | Conduct detailed requirements workshops upfront
Integration issues | Medium | Plan integration testing early and use API contracts
Performance problems | Medium | Conduct load testing and optimize before production
Security vulnerabilities | Medium | Perform security audits and implement best practices
Dependency delays | Medium | Develop detailed mitigation plan during project planning phase

## 02_AI_Project_Summary
AI PROJECT SUMMARY & RECOMMENDATIONS
EXECUTIVE NARRATIVE
Based on the uploaded Statement of Work, this initiative is classified as a GenAI / AI Implementation project requiring approximately 9 resources over 13 weeks with an estimated effort of 4680 hours. Key characteristics: • Project Type: GenAI / AI Implementation • Estimated Duration: 13 weeks (3.2 months) • Estimated Team Size: 9 people • Estimated Effort: 4680 hours • Identified Risks: 6 • Project Complexity: High
RECOMMENDED APPROACH
• Recommended Delivery Model: Agile with Scrum • Recommended Governance: Standard PMO • Recommended Team Structure: 9 FTE across Development, QA, and Operations • Critical Success Factors: Resource availability, stakeholder alignment, scope management • Top Priority Risks to Mitigate: Requirement scope creep, Integration issues • Estimated Project Budget: Based on effort and standard rates • Recommended Cadence: Weekly status meetings, bi-weekly reviews, monthly steering committee
DELIVERY METRICS
Confidence Score: 70%
Risk Exposure: High
Complexity Rating: High

## 03_Project_Details
PROJECT OVERVIEW
Project Name | Client Name (To be provided)
Client Name | Client Name (To be provided)
Project Type | GenAI / AI Implementation
Delivery Model | Hybrid
Start Date | 2026-07-07
End Date | 2026-10-06
Duration | 13 weeks
Team Size | 9
PROJECT SCOPE
Scope Statement
Project scope to be clarified by user input
ASSUMPTIONS
No assumptions defined
CONSTRAINTS
• Budget constraints as per contract
• Schedule constraints based on delivery model
• Resource availability and allocation
• Third-party dependencies
• Technology and platform limitations

## 04_Project_Roadmap
PROJECT ROADMAP
Phase | Start Date | End Date | Duration | Status | Owner | Key Deliverables | Notes
Initiation | 2026-07-07 | 2026-07-14 | 1w | Planned | TBD | TBD
Discovery | 2026-07-14 | 2026-07-21 | 1w | Planned | TBD | TBD
Design | 2026-07-21 | 2026-07-28 | 1w | Planned | TBD | TBD
Development | 2026-07-28 | 2026-08-04 | 1w | Planned | TBD | TBD
Testing | 2026-08-04 | 2026-08-11 | 1w | Planned | TBD | TBD
UAT | 2026-08-11 | 2026-08-18 | 1w | Planned | TBD | TBD
Deployment | 2026-08-18 | 2026-08-25 | 1w | Planned | TBD | TBD
Hypercare | 2026-08-25 | 2026-09-01 | 1w | Planned | TBD | TBD

## 05_Detailed_Project_Plan
DETAILED PROJECT PLAN
WBS | Phase | Task | Deliverable | Owner | Start Date | End Date | Duration | Dependency | Priority | Status | Completion % | Comments
1.0 | Initiation | Project kickoff | Kickoff memo | PM | 2026-07-07 | 2026-07-14 | 1w | None | High | Planned | 0%
2.0 | Discovery | Requirements gathering | Requirements doc | BA | 2026-07-14 | 2026-07-28 | 2w | None | High | Planned | 0%
3.0 | Design | Solution design | Design spec | Architect | 2026-07-28 | 2026-08-11 | 2w | None | High | Planned | 0%
4.0 | Development | Development | Code release | Dev Lead | 2026-08-11 | 2026-09-15 | 5w | None | High | Planned | 0%
5.0 | Testing | QA testing | Test report | QA Lead | 2026-09-15 | 2026-09-29 | 2w | None | Medium | Planned | 0%
6.0 | UAT | User acceptance | UAT sign-off | Client PM | 2026-09-29 | 2026-10-06 | 1w | None | High | Planned | 0%
7.0 | Deployment | Production deployment | Go-live report | DevOps | 2026-10-06 | 2026-10-13 | 1w | None | High | Planned | 0%
8.0 | Hypercare | Support phase | Hypercare report | PM | 2026-10-13 | 2026-10-27 | 2w | None | Medium | Planned | 0%

## 06_Gantt_Chart
PROJECT GANTT CHART
Task | Jul 2026 | Aug 2026 | Sep 2026 | Sep 2026
Initiation | ████ | ████ | ████ | ████
Discovery | ████ | ████ | ████ | ████
Design | ████ | ████ | ████ | ████
Development | ████ | ████ | ████ | ████
Testing | ████ | ████ | ████ | ████
UAT | ████ | ████ | ████ | ████
Deployment | ████ | ████ | ████ | ████
Hypercare | ████ | ████ | ████ | ████

## 07_Milestone_Tracker
MILESTONE TRACKER
Milestone ID | Description | Owner | Planned Date | Actual Date | Status | Priority | Remarks
M1 | Project Kickoff | PM | 2026-07-07 |  | Planned | High
M2 | Requirements Complete | BA | 2026-07-21 |  | Planned | High
M3 | Design Review | Architect | 2026-08-04 |  | Planned | High
M4 | Development Complete | Dev Lead | 2026-09-08 |  | Planned | High
M5 | Testing Complete | QA Lead | 2026-09-22 |  | Planned | High
M6 | UAT Sign-off | Client PM | 2026-09-29 |  | Planned | High
M7 | Go-Live | DevOps | 2026-10-06 |  | Planned | High
M8 | Hypercare Complete | PM | 2026-10-20 |  | Planned | High

## 08_Resource_Plan
RESOURCE PLAN
Resource | Role | Department | Allocation % | Start Date | End Date | Effort Hours | Utilization %
PM_1 | PM | Engineering | 100% | 2026-07-07 | 2026-10-06 | 520 | 100%
Tech Lead_1 | Tech Lead | Engineering | 100% | 2026-07-07 | 2026-10-06 | 520 | 100%
Developer_1 | Developer | Engineering | 100% | 2026-07-07 | 2026-10-06 | 520 | 100%
Developer_2 | Developer | Engineering | 100% | 2026-07-07 | 2026-10-06 | 520 | 100%
Developer_3 | Developer | Engineering | 100% | 2026-07-07 | 2026-10-06 | 520 | 100%
QA Engineer_1 | QA Engineer | Engineering | 100% | 2026-07-07 | 2026-10-06 | 520 | 100%
QA Engineer_2 | QA Engineer | Engineering | 100% | 2026-07-07 | 2026-10-06 | 520 | 100%
DevOps_1 | DevOps | Engineering | 100% | 2026-07-07 | 2026-10-06 | 520 | 100%
DevOps_2 | DevOps | Engineering | 100% | 2026-07-07 | 2026-10-06 | 520 | 100%

## 09_RAID_Register
RAID REGISTER (Risks, Assumptions, Issues, Dependencies)
Total Risks | 6
Total Assumptions | 0
Total Issues | 0
Total Dependencies | 0
ID | Type | Description | Impact | Probability | Owner | Mitigation/Action | Status
R1 | Risk | Requirement scope creep | High | Medium | TBD | Conduct detailed requirements workshops upfront | Open
R2 | Risk | Integration issues | High | Medium | TBD | Plan integration testing early and use API contracts | Open
R3 | Risk | Performance problems | High | Medium | TBD | Conduct load testing and optimize before production | Open
R4 | Risk | Security vulnerabilities | High | Medium | TBD | Perform security audits and implement best practices | Open
R5 | Risk | Dependency delays | High | Medium | TBD | Develop detailed mitigation plan during project planning phase | Open
R6 | Risk | Testing coverage gaps | High | Medium | TBD | Develop detailed mitigation plan during project planning phase | Open

## 10_RACI_Matrix
RACI MATRIX (Responsible, Accountable, Consulted, Informed)
R | Responsible - Does the work
A | Accountable - Final authority
C | Consulted - Provides input
I | Informed - Kept in the loop
Activity | PM | BA | Architect | Dev Lead | QA Lead | Client PM | DevOps
Project Kickoff | A | C | C | C | C | C | I
Requirements | C | A | C | C | I | C | I
Design Review | C | C | A | C | I | I | I
Development | C | I | C | A | I | I | I
Testing | C | I | I | C | A | I | I
UAT | C | I | I | I | C | A | I
Deployment | C | I | I | I | I | C | A
Hypercare | A | I | I | C | I | C | C

## 11_Weekly_Status
WEEKLY STATUS TRACKER
Week | Start Date | End Date | Planned % | Actual % | Variance % | Status | Comments
Week 1 | 2026-07-07 | 2026-07-13 | 7% | 0% | 0% | Pending
Week 2 | 2026-07-14 | 2026-07-20 | 15% | 0% | 0% | Pending
Week 3 | 2026-07-21 | 2026-07-27 | 23% | 0% | 0% | Pending
Week 4 | 2026-07-28 | 2026-08-03 | 30% | 0% | 0% | Pending
Week 5 | 2026-08-04 | 2026-08-10 | 38% | 0% | 0% | Pending
Week 6 | 2026-08-11 | 2026-08-17 | 46% | 0% | 0% | Pending
Week 7 | 2026-08-18 | 2026-08-24 | 53% | 0% | 0% | Pending
Week 8 | 2026-08-25 | 2026-08-31 | 61% | 0% | 0% | Pending
Week 9 | 2026-09-01 | 2026-09-07 | 69% | 0% | 0% | Pending
Week 10 | 2026-09-08 | 2026-09-14 | 76% | 0% | 0% | Pending
Week 11 | 2026-09-15 | 2026-09-21 | 84% | 0% | 0% | Pending
Week 12 | 2026-09-22 | 2026-09-28 | 92% | 0% | 0% | Pending
Week 13 | 2026-09-29 | 2026-10-05 | 100% | 0% | 0% | Pending