# STATEMENT OF WORK

Mobile Banking Application Development

# PROJECT OVERVIEW

Client: Acme Financial Services Inc.

Project Name: Mobile Banking Platform - Phase 1

Project Manager: Sarah Johnson (Acme)

Start Date: August 1, 2026

Target Completion: February 28, 2027

Duration: 6 months

# EXECUTIVE SUMMARY

Acme Financial Services requires a modern mobile banking application for iOS and Android platforms. The application will enable customers to manage accounts, transfer funds, pay bills, and access financial planning tools from their smartphones.

The primary objective is to deliver a production-ready mobile application that enhances customer engagement and reduces operational costs through digital self-service capabilities.

# PROJECT SCOPE

## DELIVERABLES (In Scope):

iOS Mobile Application (Native Swift)

Account management dashboard

Fund transfer functionality

Bill payment system

Transaction history and statements

Mobile wallet integration

Push notifications

Biometric authentication (Face ID, Touch ID)

Android Mobile Application (Native Kotlin)

Feature parity with iOS application

Material Design implementation

Offline functionality for basic features

Integration with Google Pay

Push notifications

Biometric authentication

Backend APIs

Account services API

Transaction processing API

Bill payment API

User authentication & security API

Analytics and logging API

Cloud infrastructure setup (AWS)

Security & Compliance

PCI DSS compliance certification

HIPAA compliance for personal data

Encryption protocols (TLS 1.3 minimum)

Multi-factor authentication

Session management security

# TEAM COMPOSITION

Tech Lead / Architect: 1 FTE

iOS Developers: 2 FTE

Android Developers: 2 FTE

Backend Developers: 3 FTE

QA Engineers: 2 FTE

DevOps Engineer: 1 FTE

UI/UX Designer: 1 FTE

Business Analyst: 1 FTE

Project Manager: 1 FTE

Total: 14 FTE (Full-Time Equivalents)

# KEY ASSUMPTIONS

Client will provide timely feedback and approvals

Third-party API integrations will be available

Client will conduct user acceptance testing within agreed timeframe

No major scope changes after requirements sign-off

Client infrastructure meets minimum security requirements

Team members will be available full-time throughout project

# DELIVERABLES TIMELINE

## Phase 1: Requirements & Design (Weeks 1-4)

Requirements finalization

Technical architecture design

UI/UX design mockups

Security assessment

## Phase 2: Development - Part 1 (Weeks 5-12)

Backend API development

iOS app development

Android app development

Database design and setup

## Phase 3: Development - Part 2 (Weeks 13-18)

Advanced features development

Security implementation

Performance optimization

Integration testing

## Phase 4: Testing & QA (Weeks 19-22)

Functional testing

Security testing

Performance testing

User acceptance testing

## Phase 5: Deployment & Support (Weeks 23-26)

App store submission

Production deployment

Knowledge transfer

2-week post-launch support

# PAYMENT TERMS

Total Project Cost: $1,200,000 USD

Payment Schedule:

Initial payment (20%): $240,000 upon contract signing

Milestone 1 (25%): $300,000 upon Phase 2 completion

Milestone 2 (25%): $300,000 upon Phase 4 completion

Final payment (30%): $360,000 upon production release

# CONSTRAINTS

Budget: $1.2 million

Timeline: 6 months fixed

Technology stack: Swift (iOS), Kotlin (Android), Node.js (Backend)

Compliance: Must meet PCI DSS Level 1

# KEY RISKS

Integration with legacy banking systems - Mitigation: Early integration testing

Security compliance delays - Mitigation: Early security reviews

Resource availability - Mitigation: Documented backup resources

Third-party API delays - Mitigation: Mock API development in parallel

Scope creep - Mitigation: Strict change control process